## Slide 1
Exploring School Consolidation Efforts in the
Bibb County School District for 2025-2026 School Year
Dr. Katika D. Lovett
Deputy Superintendent
July 18, 2024

## Slide 2: OUR VISION
OUR MISSION
Students are empowered to learn, lead, innovate and serve as productive and caring citizens within their chosen paths of success.
The Bibb County School District maximizes student achievement and social-emotional well-being by building a sense of community in safe, equitable learning environments.

## Slide 3: OUR GUIDING PRINCIPLES
Personalized Learning
Collaboration
Engagement
Safety
Effective Leadership
LEARNER OUTCOMES
OUR GOALS
Student Achievement
Staff Effectiveness
Stakeholder Engagement
Each student
will graduate empowered to make a well-informed decision about their next step. They will learn about themselves as they engage in rigorous content and gain exposure through personalized learning experiences, thereby enlightening them to choose their most meaningful pathway.

## Slide 5
Overview
The purpose of this presentation is to provide an in-depth overview of the proposed plan for exploring school consolidation within the Bibb County School District for the 2025-2026 school year. This plan emphasizes thorough planning, rigorous data analysis, and active community and student engagement to make informed decisions that prioritize financial efficiency and significantly enhance student outcomes and experiences.
Roadmap
Core Elements
Goals and Strategies
Timeline and Activities
Next Steps + Q &A
Takeaway
With a focus on robust planning, rigorous data analysis, and active stakeholder engagement, the Bibb County School District is poised to explore school consolidation as a key strategy for future budget planning. This comprehensive and balanced approach will empower us to make informed decisions that prioritize financial efficiency and significantly enhance student outcomes and experiences.
AGENDA

## Slide 6
CORE ELEMENTS OF THE PROCESS
Transparency: Maintain open lines of communication throughout the process, ensuring all stakeholders, especially students, are informed and heard.
Equity: Ensure that consolidation decisions do not disproportionately impact any particular group and enhance equitable access to resources and opportunities.
Student Support: Provide resources and support for students affected by the consolidation, including counseling, academic support, and extracurricular opportunities.
Financial Efficiency: Conduct a thorough analysis of potential cost savings and financial implications. Identify opportunities for increased efficiency and effectiveness through consolidation while maintaining or improving education outcomes.
Future Budget Planning: Integrate school consolidation considerations into future budget planning processes. Provide recommendations and strategies for long-term financial planning.

## Slide 7
Timeline OVERVIEW
Phase 1
  Planning
Phase 2
Data Collection and Analysis
Phase 3
Community
Phase 4
Decision
Making
Planning
Engagement
and
Feedback
and
  and
  Preparation

## Slide 8
SCHOOL CONSOLIDATION PROJECT MANAGER
A request for proposals (RFP) will be released July 2024 for a School Consolidation Project Manager.
Based on research-based best practices, engaging a consultant in this work is the most advantageous route to achieve high-quality results and in fairness to an objective approach to this effort.
However, as a further effort to accomplish the task of decision-making on consolidation and as a cost-saving measure, the District is prepared to enlist a project manager to lead and facilitate this task up to a final decision.
This will not require an entire year and will allow the District to continue its focus on priorities in concert with this significant effort.

## Slide 9
GOALS AND STRATEGIES
Comprehensive Financial Assessment:
Objective: Conduct a comprehensive assessment of the potential cost savings and financial implications of school consolidation within the Bibb County School District.
Actions:
  Review historical financial data, current expenditures, and projected costs.
  Analyze potential savings from reduced administrative costs, facility maintenance, and operational efficiencies.
Resource Allocation Analysis:
Objective: Analyze the current allocation of resources and expenditures across the district’s schools and administrative functions.
Action:
  Maps out current resource distribution, identifying areas of inefficiency or redundancy.
  Evaluate the impact of resource allocation on student outcomes and opportunities.
Efficiency and Effectiveness:
Objective: Identify opportunities for increased efficiency and effectiveness through consolidation while maintaining or improving educational outcomes.
Actions:
  Develop scenarios that optimize facility usage and staff allocations.
  Ensure that consolidation plans enhance or preserve the quality of education and student support services.
Integration into Budget Planning:
Objective: Provide recommendations and strategics for integrating school consolidation considerations into future budget planning processes.
Actions:
  Develop a long-term financial plan that incorporates consolidation benefits.
  Create a framework for continuous monitoring and evaluation of financial and educational outcomes post-consolidation.

## Slide 10
TIMELINE AND KEY ACTIVITIES
Phase 1: Planning and Preparation (July-August 2024)
July 2024:
Form a Steering Committee:
  Include key stakeholders: school board members, principals, teachers, parents, students, community leaders, financial experts, and representatives from local government.
Define Goals and Objectives:
  Focus on enhancing student academic achievement, ensuring equitable access to resources, optimizing facility use, and achieving cost savings.
Develop a Communication Plan:
  Establish channels for regular updates and feedback, such as a dedicated website, newsletters, social media platforms, and town hall meetings.
Initial Community Engagement:
  Conduct community forums to understand their concerns and aspirations regarding school consolidation.
August 2024:
Conduct Initial Research:
  Review existing data on school performance, student enrollment, facilities, transportation, and budget.
Engage a Cross-Functional Team:
  Identify internal team of experts in school consolidation, student outcomes, and financial analysis to provide insights and guidance.
Develop a Project Plan:
  Outline key milestones, deliverables, and responsibilities, with a focus on student impact and financial analysis.

## Slide 11
Phase 2: Data Collection and Analysis (September-November 2024)
September 2024:
Conduct Surveys and Focus Groups:
  Gather input from students, parents, teachers, and the community about their concerns and expectations. Ensure diverse student voices are heard.
Facility Assessments:
  Evaluate the condition and capacity of current school buildings, focusing on the impact on the student learning environment.
Financial Analysis:
  Conduct a comprehensive assessment of potential cost savings and financial implications of consolidation.
  Analyze current expenditures and resource allocation across schools and administrative functions.
October 2024:
Analyze Enrollment Trends:
  Project future enrollment patterns and identify schools with declining or increasing numbers. Consider the implications for student diversity and inclusivity.
Budget Analysis:
  Review financial implications and potential cost savings of consolidation, prioritizing resources for student programs and support services.
November 2024:
Develop Preliminary Scenarios:
  Create multiple consolidation and non-consolidation models based on collected data, emphasizing the impact on student outcomes, financial implications, and community sentiment.
  Conduct a detailed analysis of the advantages and disadvantages of each scenario, including impacts on student achievement, community cohesion, operational efficiency, and financial health.
Present Findings to Steering Committee:
  Review data and preliminary scenarios for feedback and refinement, ensuring student representatives are actively involved.

## Slide 12
Phase 3: Community Engagement and Feedback (December 2024-February 2025)
December 2024:
Host Community Forums:
  Present preliminary scenarios to the public and gather feedback, with specific sessions for students and parents. Provide detailed pros and cons for each scenario.
Launch an Online Feedback Platform:
  Allow community members, especially students, to submit comments and suggestions online.
January 2025:
Conduct Additional Focus Groups:
  Focus on areas with high impact from consolidation to understand specific concerns, particularly from students and families.
Refine Scenarios:
  Incorporate community and student feedback into revised models, ensuring a balanced view of consolidation and non-consolidation options.
February 2025:
Publish Revised Scenarios:
  Share updated models with detailed pros and cons, focusing on student benefits and addressing concerns.
Community Survey:
  Conduct a comprehensive survey to gauge public opinion on revised scenarios, with a focus on student perspectives.

## Slide 13
TIMELINE AND KEY ACTIVITIES CONT.
Phase 4: Decision Making and Planning (March-May 2025)
March 2025:
Steering Committee Review:
  Finalize the consolidation and non-consolidation plans based on community feedback and data analysis, ensuring student representatives are part of the decision-making process.
Board Approval:
  Present the final plan to the school board for approval, highlighting student-centered outcomes and benefits of each option.
April 2025:
Develop Implementation Plan:
  Create a detailed timeline and action steps for the consolidation process if necessary, ensuring minimal disruption to students.
Communicate Final Decision:
  Inform all stakeholders about the approved plan and next steps, with targeted communications for students and families.
May 2025:
Prepare for Transition:
  Begin logistical preparations for the 2025-2026 school year, including student transportation, reassignments, and support services.
Ongoing Community Engagement:
  Continue to update the community and address any concerns, with a focus on supporting students through the transition.

## Slide 14
STEERING COMMITTEE INVITATION
Dear Bibb County School District Stakeholders,
We are pleased to invite you to participate in the formation of a new Steering Committee dedicated to exploring the potential for school consolidation within the Bibb County School District. Your expertise, insight, and commitment to our community are invaluable as we consider the future of our schools and strive to enhance the educational experience for all students.
Purpose of the Steering Committee:
The Steering Committee will be tasked with evaluating the feasibility, benefits, and challenges of consolidating schools within our district. This process aims to optimize resources, improve educational outcomes, and ensure the sustainability of our school system.
Key Objectives:
1. Assess current school capacities and utilization rates.
2. Analyze demographic trends and projected student enrollment.
3. Evaluate potential impacts on student transportation, staffing, and community engagement.
4. Develop a comprehensive consolidation plan with stakeholder input.
Committee Composition:
- Parents and Guardians
- Teachers and School Staff
- District Administrators
- Local Government Representatives
- Community and Business Leaders
- Students
If you are interested in serving on the Steering Committee or would like more information, please accessing the QR code or link at https://forms.office.com/r/Z9wYXYV9Qi. In your response, please include your name, affiliation, and a brief statement of your interest in participating. We believe that the diverse perspectives of our community members will be crucial in shaping the future of our schools. Your participation will help ensure that any decisions made are in the best interests of our students and the broader community.

## Slide 15
NEXT STEPS
Recruit Steering Committee Members
Release RFP for School Consolidation Project Manager

## Slide 16
Q&A