## Slide 1
Exploring School Consolidation Efforts in the
Bibb County School District for 2025-2026 School Year:
October 2024 Update
Dr. Katika D. Lovett, Deputy Superintendent
Thelron Pleas, Towering Your Success
October 17, 2024

## Slide 2
Overview
The purpose of this presentation is to provide an update on the proposed plan for exploring school consolidation within the Bibb County School District for the 2025-2026 school year.
Roadmap
Core Elements
Goals and Strategies
Timeline and Activities
BCSD Steering Committee Overview
Project Management Updates
Q &A
Takeaway
With a focus on robust planning, rigorous data analysis, and active stakeholder engagement, the Bibb County School District is poised to explore school consolidation as a key strategy for future budget planning. This comprehensive and balanced approach will empower us to make informed decisions that prioritize financial efficiency and significantly enhance student outcomes and experiences.
AGENDA

## Slide 3: OUR MISSION
OUR VISION
Students are empowered to learn, lead, innovate and serve as productive and caring citizens within their chosen paths of success.
The Bibb County School District maximizes student achievement and social-emotional well-being by building a sense of community in safe, equitable learning environments.

## Slide 4: OUR GUIDING PRINCIPLES
Personalized Learning
Collaboration
Engagement
Safety
Effective Leadership
LEARNER OUTCOMES
OUR GOALS
Student Achievement
Staff Effectiveness
Stakeholder Engagement
Each student
will graduate empowered to make a well-informed decision about their next step. They will learn about themselves as they engage in rigorous content and gain exposure through personalized learning experiences, thereby enlightening them to choose their most meaningful pathway.

## Slide 6
CORE ELEMENTS OF THE PROCESS
Transparency: Maintain open lines of communication throughout the process, ensuring all stakeholders, especially students, are informed and heard.
Equity: Ensure that consolidation decisions do not disproportionately impact any particular group and enhance equitable access to resources and opportunities.
Student Support: Provide resources and support for students affected by the consolidation, including counseling, academic support, and extracurricular opportunities.
Financial Efficiency: Conduct a thorough analysis of potential cost savings and financial implications. Identify opportunities for increased efficiency and effectiveness through consolidation while maintaining or improving education outcomes.
Future Budget Planning: Integrate school consolidation considerations into future budget planning processes. Provide recommendations and strategies for long-term financial planning.

## Slide 7
GOALS AND STRATEGIES
Comprehensive Financial Assessment:
Objective: Conduct a comprehensive assessment of the potential cost savings and financial implications of school consolidation within the Bibb County School District.
Actions:
  Review historical financial data, current expenditures, and projected costs.
  Analyze potential savings from reduced administrative costs, facility maintenance, and operational efficiencies.
Resource Allocation Analysis:
Objective: Analyze the current allocation of resources and expenditures across the district’s schools and administrative functions.
Action:
  Maps out current resource distribution, identifying areas of inefficiency or redundancy.
  Evaluate the impact of resource allocation on student outcomes and opportunities.
Efficiency and Effectiveness:
Objective: Identify opportunities for increased efficiency and effectiveness through consolidation while maintaining or improving educational outcomes.
Actions:
  Develop scenarios that optimize facility usage and staff allocations.
  Ensure that consolidation plans enhance or preserve the quality of education and student support services.
Integration into Budget Planning:
Objective: Provide recommendations and strategics for integrating school consolidation considerations into future budget planning processes.
Actions:
  Develop a long-term financial plan that incorporates consolidation benefits.
  Create a framework for continuous monitoring and evaluation of financial and educational outcomes post-consolidation.

## Slide 8
Timeline OVERVIEW
Phase 1
  Planning
Phase 2
Data Collection and Analysis
Phase 3
Community
Phase 4
Decision
Making
Planning
Engagement
and
Feedback
and
  and
  Preparation

## Slide 9
TIMELINE AND ACTIVITIES (updated)
Phase 2: Data Collection and Analysis (September-December 2024)
September-Ongoing:
Conduct Surveys and Focus Groups:
  Gather input from students, parents, teachers, and the community about their concerns and expectations. Ensure diverse student voices are heard.
Facility Assessments:
  Evaluate the condition and capacity of current school buildings, focusing on the impact on the student learning environment.
Financial Analysis:
  Conduct a comprehensive assessment of potential cost savings and financial implications of consolidation.
  Analyze current expenditures and resource allocation across schools and administrative functions.
October-November 2024:
Analyze Enrollment Trends:
  Project future enrollment patterns and identify schools with declining or increasing numbers. Consider the implications for student diversity and inclusivity.
Budget Analysis:
  Review financial implications and potential cost savings of consolidation, prioritizing resources for student programs and support services.
November-December 2024:
Develop Preliminary Scenarios:
  Create multiple consolidation and non-consolidation models based on collected data, emphasizing the impact on student outcomes, financial implications, and community sentiment.
  Conduct a detailed analysis of the advantages and disadvantages of each scenario, including impacts on student achievement, community cohesion, operational efficiency, and financial health.
Present Findings to Steering Committee:
  Review data and preliminary scenarios for feedback and refinement, ensuring student representatives are actively involved.

## Slide 10
BCSD SCHOOL CONSOLIDATION STEERING COMMITTEE
The purpose of the BCSD School Consolidation Committee is to carefully evaluate the current structure and resources of our school district, with the goal of improving educational opportunities, operational efficiency, and financial sustainability.
The committee will analyze enrollment trends, facility usage, academic programs, and community needs to provide informed recommendations to the school board, prioritizing the best interests of students, staff, and the community.

## Slide 11
STEERING COMMITTEE COMPOSITION
The School Consolidation Steering Committee is composed of representatives from various stakeholder groups to ensure diverse perspectives and equitable representation. The breakdown of the committee members is as follows:
Teachers (9): Includes representatives from different grade levels and subject areas.
Parents (10): Represents families from different schools affected by the consolidation.
Business Leaders (7): Local business community representatives who can provide insights into economic impacts and opportunities.
Community and Faith-Based Leaders (5): Representatives from community organizations and religious institutions to offer perspectives on social and community impacts.
Central Office Leaders (9): District administrators with expertise in areas such as student affairs, teaching and learning, finance, operations, data, and human resources.
School-Based Leaders (10): Principals and assistant principals from throughout the district.
Students (3): Student representatives from different grade levels to provide first-hand perspectives on the impact of consolidation.
Elected Officials (2)

## Slide 12
PROJECT MANAGEMENT UPDATES
Phase I:
Planning and Preparation
Strategic Project Management Meetings
September 16th
September 17th
September 25th
October 2nd
October 16th
Steering Committee Agenda Development and Meeting Facilitation
Finalization of Project Management Plan
Phase II:
School and District Data Collection
Local, State, and Federal Data Collection
Quantitative and Qualitative Instrument Development
Data Collection and Analysis
Conduct Initial Educational Research

## Slide 13
STEERING COMMITTEE MEETING DATES
Monday, October 21, 2024 @ PLC
Monday, November 11, 2024 @ PLC
Monday, December 9, 2024 @ PLC
Monday, January 6, 2025 @ PLC
Monday, February 10, 2025 @ PLC
Tuesday, March 11, 2025 @ Thompson Stadium Complex
All meetings will take place from 5:00 PM-7:00 PM

## Slide 14
Q&A