## SPLOST Schedule
|  |  |  | SPLOST Schedule FY24 | [11 empty] | SCHEDULE "12"
[10 empty] | AMOUNT |  | AMOUNT
[6 empty] | ORIGINAL |  | CURRENT |  | EXPENDED |  | EXPENDED |  | TOTAL |  | ESTIMATED
[6 empty] | ESTIMATED |  | ESTIMATED |  | IN CURRENT |  | IN PRIOR |  | COMPLETION |  | COMPLETION
PROJECT | [5 empty] | COST (1) |  | COSTS (2) |  | YEAR (3) (4) |  | YEARS (3) (4) |  | COST |  | DATE
2012 Sales Tax - Authorized Projects
1 | Americans with Disabilities Act (ADA) Improvements |  |  |  | $ | 2342500 | $ | 15044323.5 | $ | 2728.1 | $ | 15041595.4 | $ | 15044323.5 |  | Completed
2 | Stadiums |  |  |  |  | 9557400 |  | 10628646.65 |  |  |  | 10628646.65 |  | 10628646.65 |  | Completed
3 | Capital Renewal Program |  |  |  |  | 84892200 |  | 97547198.89 |  | 27432.31 |  | 94175155.66 |  | 94202587.97 |  | Completed
4 | Code Requirements |  |  |  |  | 2342500 |  | 2677726.34 |  |  |  | 2677726.34 |  | 2677726.34 |  | Completed
5 | Coralwood Diagnostic Center Addition |  |  |  |  | 9932200 |  | 6164482.54 |  |  |  | 6164482.54 |  | 6164482.54 |  | Completed
6 | Early Learning Center |  |  |  |  | 2717300 |  | 2188329.76 |  |  |  | 2188329.76 |  | 2188329.76 |  | Completed
7 | Arts School at former Avondale MS |  |  |  |  | 4029100 |  | 11127167 |  |  |  | 310896.41 |  | - |  | 2028-06-01
8 | Renovation of Southwest DeKalb HS & Stone Mountain HS |  |  |  |  | 11056600 |  | 34163839.27 |  |  |  | 34163839.27 |  | 34163839.27 |  | Completed
9 | Replacement of Austin ES, Fernbank ES, Gresham Park ES,
| Pleasantdale ES, Peachcrest ES, Rockbridge ES, Smoke Rise ES |  |  |  |  | 135021700 |  | 172480185.67 |  | 121106.71 |  | 169675372.86 |  | 169796479.57 |  | Completed
10 | Henderson MS Renovation/Addition |  |  |  |  | 14992000 |  | 19245872.25 |  |  |  | 19245872.25 |  | 19245872.25 |  | Completed
11 | Redan HS Renovation/Addition |  |  |  |  | 20988800 |  | 22065648.16 |  |  |  | 22065648.16 |  | 22065648.16 |  | Completed
12 | Chamblee HS Replacement |  |  |  |  | 55001900 |  | 69089766.52 |  | 5810912.5 |  | 63278854.02 |  | 69089766.52 |  | Completed
13 | McNair MS Replacement |  |  |  |  | 35043800 |  | 40742607.53 | 9000 |  |  | 40733607.53 |  | 40733607.53 |  | Completed
14 | Local School Priority Requests |  |  |  |  | 5153500 |  | 2902294.25 |  |  |  | 2902294.25 |  | 2902294.25 |  | Completed
15 | Demolition |  |  |  |  | 2342500 |  | 4221328.66 |  |  |  | 4221328.66 |  | 4221328.66 |  | Completed
16 | Safety/Security Systems Upgrade |  |  |  |  | 2342500 |  | 2292719.24 |  |  |  | 2292719.24 |  | 2292719.24 |  | Completed
17 | Technology Equipment & Infrastructure Refresh |  |  |  |  | 36261900 |  | 33277357.33 |  |  |  | 33277357.33 |  | 33277357.33 |  | Completed
18 | School Buses |  |  |  |  | 9463700 |  | 12800247.61 |  |  |  | 12800247.61 |  | 12800247.61 |  | Completed
19 | Service Vehicles |  |  |  |  | 1592900 |  | 2252530.33 |  |  |  | 2252530.33 |  | 2252530.33 |  | Completed
20 | Other capital improvements & supporting services (includes
Bond Series 2012 Bond Issuance Costs, Principal Payments,
| and 2011 COPs Interest Payments) |  |  |  |  | 29925000 |  | 82132562.14 |  | 1819.89 |  | 80269196.14 |  | 80271016.03 |  | Completed
[5 empty] | $ | 475000000 | $ | 643044833.64 | $ | 5972999.51 | $ | 618365700.41 | $ | 624018803.51
[10 empty] | AMOUNT |  | AMOUNT
[6 empty] | ORIGINAL |  | CURRENT |  | EXPENDED |  | EXPENDED |  | TOTAL |  | ESTIMATED
[6 empty] | ESTIMATED |  | ESTIMATED |  | IN CURRENT |  | IN PRIOR |  | COMPLETION |  | COMPLETION
PROJECT | [5 empty] | COST (1) |  | COSTS (2) |  | YEAR (3) (4) |  | YEARS (3) (4) |  | COST |  | DATE
2017 Sales Tax - Authorized Projects
1 | Making of site, facility and technology improvements
deemed necessary to improve safety and security, such as
enhancing surveillance systems, fire alarm systems, fire
sprinkler installation, perimeter fencing, etc. at some or all
of the DeKalb County School District (DCSD) schools and
| facilities; |  |  |  | $ | 12872000 | $ | 41245876 | $ | 1481120.05 | $ | 9071921.475 | $ | - |  | 2026-06-30
2 | Adding to, modifying, replacing, reconfiguring schools and/or
creating new schools and/or facilities to accommodate
current and future student enrollment, address major facility
conditions, develop early childhood centers, enhance
regional support of schools, and accomodate expanded new
programmatic needs, and acquiring land for constructing and
equipping new and/or replacement schools/facilities, or
equivalent facility capactiy, including, but not limited to, site
preparation and the demolition of all or portions of existing
structures and/or acquiring leasehold purchasing of
facilities/properties as needed based on DCSD's
| determination of need priorities; |  |  |  |  | 298180000 |  | 260642220 |  | 6414172.84 |  | 128188034.58 |  | - |  | 2028-06-30
3 | Adding to, renovating, modifying, reconfiguring, equipping,
upgrading, supplementing, acquiring, replacing, and
installing capital improvements for various existing and new
schools, buildings and facilities (including schools, buildings
and facilities to be constructed pursuant to this resolution,
once completed and including any site preparation and
demolition of existing structures if necessary) e.g., roofing,
plumbing, wiring, painting, water piping, HVAC, making
athletic field and physical education facility upgrades and
improvements, ADA renovations, infrastructure improvements,
repaving, restroom facilities, systems for environmental and
air quality control, physical education facilities, kitchens,
improvements to comply with health, safety and applicable
building codes, traffic control and optimization, parking and
parking capacity, stormwater management facilities, and
program-driven modifications, as needed based on the
| DCSD's determination of need priorities; |  |  |  |  | 96948000 |  | 184311643 |  | 69328444.51 |  | 45184718.89 |  | - |  | 2028-06-01
4 | Making technology improvements, by acquiring, replacing,
purchasing, installing, upgrading or supplementing
technology including, but not limited to technology that
supports and/or enhances instruction, digital communication
technology, enhanced school security solutions, wireless
technology, enterprise content management solutions,
replacement and/or enhancement of technology/systems in
support of an Enterprise Resource Planning (ERP) upgrade,
data storage systems, telecommunication systems, digital
records retention, technology hardware, software, and related
infrastructure at some or all of the DCSD schools and
| facilities, as needed; |  |  |  |  | 65000000 |  | 71500000 |  | 882920.43 |  | 63238978.52 |  | - |  | 2025-06-30
5 | Replacing, purchasing, upgrading, refurbishing or
supplementing school buses and support vehicles and other
capital equipment as needed including, but not limited to
items such as desks, chairs, tables, instructional equipment,
band equipment, kitchen equipment, waste compactors,
portable classroom/modular buildings, custodial equipment,
grounds equipment, etc. at some or all DCSD schools and
| facilities; |  |  |  |  | 40000000 |  | 40312169 |  | 1070466.33 |  | 35371541.21 |  | - |  | 2026-06-30
6 | and the expenses incidental to accomplishing the DeKalb
projects including, but not limited to, implementation
| expenses, management expenses, and legal expenses. |  |  |  |  | 48000000 |  | 32288092 |  | 99474.1 |  | 30458719.03 |  | - |  | 2028-06-30
[5 empty] | $ | 561000000 | $ | 630300000 | $ | 79276598.26 | $ | 311513913.705 | $ | 0
[10 empty] | AMOUNT |  | AMOUNT
[6 empty] | ORIGINAL |  | CURRENT |  | EXPENDED |  | EXPENDED |  | TOTAL |  | ESTIMATED
[6 empty] | ESTIMATED |  | ESTIMATED |  | IN CURRENT |  | IN PRIOR |  | COMPLETION |  | COMPLETION
PROJECT | [5 empty] | COST (1) |  | COSTS (2) |  | YEAR (3) (4) |  | YEARS (3) (4) |  | COST |  | DATE
2021 Sales Tax - Authorized Projects
1 | Adding to, upgrading, reconfiguring, renovating, replacing, modifying and
equipping existing and replacement schools, support facilities, athletic fields
| and physical education facilities; |  |  |  | $ | 150000000 | $ | 28000000 | $ | 3869848.21 | $ | 2835661.75 | $ | 0 |  | 2028-06-01
2 | Acquiring and developing land for, constructing and equipping, new and
replacement schools and support facilities, as well as additions to existing
| facilities; |  |  |  |  | 352000000 |  | 516150000 |  | 2731003.8 |  | 0 |  | 0 |  | 2028-01-31
3 | Installing capital improvements for various existing and new schools,
| buildings and facilities; |  |  |  |  | 69000000 |  | 128750000 |  | 0 |  | 0 |  | 0 |  | 2028-01-31
4 | Providing hardware, software, and related infrastructure and making
| technology improvements; |  |  |  |  | 129000000 |  | 95000000 |  | 2173429.08 |  | 0 |  | 0 | 2023-01-28 | 2028-01-31
5 | Replacing, purchasing, upgrading school buses, support vehicles, and other
| capital equipment |  |  |  |  | 40000000 |  | 35500000 |  | 0 |  | 0 |  | 0 | 2023-01-28 | 2028-01-31
[5 empty] | $ | 740000000 | $ | 803400000 | $ | 8774281.09 | $ | 2835661.75 | $ | 0
[5 empty] | $ | 1776000000 | $ | 2076744833.64 | $ | 94023878.86 | $ | 932715275.865 | $ | 624018803.51
|  | -1 | The School District's original cost estimate as specified in the resolution calling for the imposition of the Local Option Sales Tax.
|  | -2 | The School District's current estimate of total cost for the projects. Includes all cost from project inception to completion.
|  | -3 | The voters of DeKalb County approved the imposition of a 1% sales tax to fund the above projects and retire associated debt. Amounts expended for these projects may include
sales tax proceeds, state, local property taxes and/or other funds over the life of the projects.