## FY24 byProject
Project Number | Category | Project Name | FY 23 Original Estimated Cost | FY 24 Current Estimated Cost (EAC) | Current Year Expenditure | Prior Years Expenditure | Total Expended | Project Status | Estimated Construction Finish
00035 | 6 | 000. Revenue Deposit Fund | 0 | 0 | 0 | 0 | 0
10135 | 1 | 101. Sprinkler Installation A | 1230000 | 739667 | 0 | 437684.49 | 437684.49
10235 | 1 | 102. Sprinkler Installation B | 1250000 | 859939 | 249177.62 | 521360.68 | 770538.3
10335 | 1 | 103. Sprinkler Installation C | 1420000 | 708725 | 0 | 555296.16 | 555296.16
10935 | 1 | 109. Life Safety Set-aside | 3530000 | 0 | 0 | 1050.06 | 1050.06
11135 | 1 | 111. Fence installation A | 803000 | 406808 | 0 | 406808 | 406808
11235 | 1 | 112. Fence installation B | 916000 | 380260 | 0 | 380260 | 380260
11335 | 1 | 113. Fence installation C | 751000 | 376348 | 0 | 376348 | 376348
11435 | 1 | 114. Athletic Field Fencing | 0 | 969030.18 | 983.8 | 914520.18 | 915503.98
11535 | 1 | 115. Security Vestibules A | 917000 | 3210902 | 76572.99 | 2404731.36 | 2481304.35 | Construction | 2025-03-31
11635 | 1 | 116. Security Vestibules B | 1069000 | 2390902 | 762453.87 | 1048787.74 | 1811241.61
12135 | 1 | 121. Druid Hills HS | 616000 | 623615.03 | 0 | 623615.03 | 623615.03
12235 | 1 | 122. Hambrick ES | 370000 | 1812972 | 391931.77 | 968962.8 | 1360894.57
20135 | 2 | 201. Cross Keys HS | 10005000 | 310973.47 | 0 | 310973.47 | 310973.47
20235 | 2 | 202. Freedom MS | 8485000 | 400000 | 31823.44 | 351946.91 | 383770.35
20335 | 2 | 203. Peachtree MS | 14100000 | 228090.33 | 0 | 228090.33 | 228090.33
21135 | 2 | 211. Cedar Grove HS | 6030000 | 12100000 | 132500.41 | 11623989.1 | 11756489.51
21235 | 2 | 212. Chamblee HS | 21540000 | 795695.74 | 0 | 795695.74 | 795695.74
21335 | 2 | 213. Clarkston HS | 18040000 | 3200000 | 0 | 1341282 | 1341282 | Construction | 2025-10-31
21435 | 2 | 214. New Cross Keys HS | 84800000 | 147466000 | 1799833.99 | 1521213.63 | 3321047.62 | Design | 2027-01-04
21535 | 2 | 215. Dunwoody HS | 17690000 | 1284135.35 | 0 | 1284135.35 | 1284135.35
21635 | 2 | 216. Lakeside HS | 26990000 | 1498673.04 | 0 | 1498673.04 | 1498673.04
21735 | 2 | 217. Design New Sequoyah MS & HS | 0 | 14000000 | 3405200 | 868328.41 | 4273528.41 | - | -
22135 | 2 | 221. John Lewis ES | 31500000 | 31409071.17 | 0 | 31409071.17 | 31409071.17
22235 | 2 | 222. New ES for Cross Keys North | 30500000 | 38192451.65 | 0 | 38192451.65 | 38192451.65
22335 | 2 | 223. Indian Creek ES | 28500000 | 39855023.51 | 0 | 39855023.51 | 39855023.51
22435 | 2 | 224. New Dunwoody / Chamblee ES | 0 | 6949828.77 | 1044815 | 5643020.77 | 6687835.77
30135 | 3 | 301. Turf Installation A | 5320000 | 6729075.89 | 0 | 6729075.89 | 6729075.89
30235 | 3 | 302. Turf Installation B | 5510000 | 6806723.35 | 0 | 6806723.35 | 6806723.35
30335 | 3 | 303. Set aside for Track with Turf Installation | 0 | 0 | 0 | 0 | 0
30435 | 3 | 304. Baseball facilities improvements at Druid Hills MS and Redan HS | 0 | 2762972 | 439706.79 | 2150638.58 | 2590345.37
31135 | 3 | 311. Playground replacement | 1311000 | 1255163.3 | 0 | 1255163.3 | 1255163.3
32135 | 3 | 321. Plumbing fixture replacement | 1917000 | 412791 | 0 | 412791 | 412791
32235 | 3 | 322. Redan MS | 807000 | 8053162 | 3036805.81 | 569195.78 | 3606001.59 | Design | 2025-12-31
33135 | 3 | 331. Water Quality Set-Aside | 923000 | 0 | 0 | 0 | 0
34135 | 3 | 341. Accessibility improvements and plumbing fixtures at 4 schools | 1593000 | 170981.25 | 0 | 155153.44 | 155153.44
34235 | 3 | 342. ADA restroom upgrades | 402000 | 611471 | 0 | 552862.62 | 552862.62
34335 | 3 | 343. Druid Hills MS | 855000 | 1907328 | 1348694.72 | 60028.93 | 1408723.65 | Closeout | 2024-08-01
34435 | 3 | 344. Midvale ES | 516000 | 9774984 | 7051092.31 | 119629.1 | 7170721.41 | Construction | 2024-12-27
34535 | 3 | 345. Former John Lewis Facility | 0 | 1929006 | 422076.23 | 1440147.93 | 1862224.16 | Complete | 2020-08-01
35135 | 3 | 351. Henderson Mill ES | 7020000 | 8807300 | 4713568.52 | 265833.2 | 4979401.72 | Design | 2024-12-31
35235 | 3 | 352. Toney ES | 6790000 | 7290000 | 76034 | 198395 | 274429 | Closeout | 2026-12-30
35335 | 3 | 353. Former Nancy Creek | 6045000 | 13871073 | 459544.03 | 575226.85 | 1034770.88 | Design | 2025-07-31
35435 | 3 | 354. E. L. Miller ES | 4243000 | 8500000 | 5481250.46 | 2387974.22 | 7869224.68 | Closeout | 2024-08-01
35535 | 3 | 355. Stoneview ES | 4860000 | 15000000 | 0 | 318427.94 | 318427.94 | Construction | 2027-07-30
35635 | 3 | 356. Cary Reynolds ES | 5635000 | 12040 | 0 | 12040 | 12040
35735 | 3 | 357. Briar Vista ES | 4160000 | 4715100 | 2673471.55 | 146850 | 2820321.55 | Construction | 2025-08-28
35835 | 3 | 358. Champion Theme MS | 6063000 | 30000000 | 640362.09 | 311773.01 | 952135.1 | Closeout | 2026-07-01
35935 | 3 | 359. Livsey ES | 4100000 | 9000000 | 229385.75 | 140 | 229525.75 | Construction | 2026-12-30
36035 | 3 | 360. DeKalb HS of Technology-South | 3860000 | 10647500 | 6505818.51 | 173854.3 | 6679672.81 | Closeout | 2025-04-11
36135 | 3 | 361. Fairington ES | 2439000 | 6294787 | 2978097.26 | 627217.76 | 3605315.02 | Construction | 2025-07-31
36235 | 3 | 362. Dresden ES | 3570000 | 3783140 | 1544250 | 279081.25 | 1823331.25 | - | -
36335 | 3 | 363. Kingsley ES | 2610000 | 3610000 | 2250 | 32500 | 34750 | Closeout | 2026-05-11
36435 | 3 | 364. Hawthorne ES | 4510000 | 10178350 | 5554853.22 | 181054.47 | 5735907.69 | Construction | 2024-11-29
36535 | 3 | 365. Salem MS | 4530000 | 12013551 | 5090521.92 | 2257475.27 | 7347997.19 | Design | 2025-12-31
36635 | 3 | 366. Rock Chapel ES | 3210000 | 12000000 | 98592.5 | 119790 | 218382.5 | Construction | 2027-07-30
36735 | 3 | 367. Set-aside for Additional Contingency for Capital Renewal Projects | 0 | 0 | 0 | 0 | 0
36835 | 3 | 368. Laurel Ridge ES | 0 | 12092265 | 7419882.5 | 1921078.25 | 9340960.75 | Closeout | 2024-08-01
36935 | 3 | 369. Woodridge ES | 0 | 10060000 | 6762439.25 | 309591.27 | 7072030.52 | Closeout | 2024-08-01
37035 | 3 | 370. Chesnut ES | 0 | 9080000 | 6065437.59 | 269162.52 | 6334600.11 | Closeout | 2024-08-01
37135 | 3 | 371. Bus Parking Pavement | 2570000 | 2544373.2 | 0 | 2544373.2 | 2544373.2
37235 | 3 | 372. Ashford Park ES | 0 | 1240870.58 | 0 | 1240870.58 | 1240870.58
37335 | 3 | 373. Montgomery ES | 0 | 0 | 0 | 0 | 0
37435 | 3 | 374. Brockett ES | 0 | 1423092.52 | 0 | 1423092.52 | 1423092.52
37535 | 3 | 375. Wynbrooke ES | 0 | 1828761.11 | 0 | 1828761.33 | 1828761.33
37635 | 3 | 376. Browns Mill ES | 0 | 0 | 0 | 0 | 0
37735 | 3 | 377. DeKalb Alternative/East Campus | 0 | 2063428.17 | 0 | 2063428.17 | 2063428.17
37835 | 3 | 378. Oak Grove ES | 0 | 1462877.02 | 0 | 1462877.02 | 1462877.02
37935 | 3 | 379. Update HVAC Controls | 0 | 0 | 0 | 220 | 220
38035 | 3 | 380. Green Forrest Drive | 0 | 6000000 | 684064.5 | 1495437 | 2179501.5 | Construction | 2025-08-08
38135 | 3 | 381. Parking Addition | 1579000 | 7433026 | 50245 | 1594207.5 | 1644452.5 | Construction | 2025-12-31
38235 | 3 | 382. Set aside or resurfacing existing parking at parking addition schools | 0 | 0 | 0 | 0 | 0
40135 | 4 | 401. Technology: ERP/Finance/HR System (Bond, Initial Capital) | 2000000 | 2048859.99 | 0 | 2048859.99 | 2048859.99
40235 | 4 | 402. Technology: ERP/Finance/HR System (Sales Tax and State Reimbursements) | 10000000 | 15598364.25 | 882920.43 | 15625864.25 | 16508784.68
41135 | 4 | 411. Technology: Computer Refresh A (Bond) | 13000000 | 12958876.4 | 0 | 12958876.4 | 12958876.4
41235 | 4 | 412. Technology: Computer Refresh B (Sales Tax and State Reimbursements) | 9000000 | 12206049.01 | 0 | 12300454.01 | 12300454.01
42135 | 4 | 421. Technology: Telecommunications Upgrade | 6000000 | 5000208.47 | 0 | 5000208.47 | 5000208.47
43135 | 4 | 431. Technology: Safety and Security | 10000000 | 9578885.48 | 0 | 9578885.48 | 9578885.48
44135 | 4 | 441. Technology: Active Boards A (Bonds) | 2000000 | 1821400 | 0 | 1821399.73 | 1821399.73
44235 | 4 | 442. Technology: Active Boards B (Sales Tax and State Reimbursements) | 8000000 | 5806076.34 | 0 | 5806076.34 | 5806076.34
45135 | 4 | 451. Technology: Infrastructure | 5000000 | 3569667.35 | 0 | 3569667.35 | 3569667.35
50135 | 5 | 501. School Bus Purchase A (Bond) | 20573900 | 20386642 | 0 | 20386642 | 20386642
50235 | 5 | 502. School Bus Purchase B (Sales Tax and State Reimbursements) | 4575100 | 4486043 | 0 | 4486043 | 4486043
51135 | 5 | 511. Support Vehicle Purchase | 1483000 | 1508052.6 | 0 | 1508052.6 | 1508052.6
52135 | 5 | 521. Music Instruments | 10000000 | 10000000 | 1070466.33 | 5623295.44 | 6693761.77 | - | -
53135 | 5 | 531. Portables | 2199000 | 2436168.95 | 0 | 2436168.95 | 2436168.95
54135 | 5 | 541. Small Kitchen Equipment | 1169000 | 1148112.23 | 0 | 1148112.23 | 1148112.23
60135 | 6 | 601. Bond Costs | 8400000 | 8400000 | 0 | 893683.385 | 893683.385
60235 | 6 | 602. Program Contingency | 20600000 | 0 | 0 | 0 | 0 | - | -
60335 | 6 | 603. DCSD Salary | 5000000 | 5000000 | -13994.15 | 4775972.14 | 4761977.99
60435 | 6 | 604. General Services | 1000000 | 1320000 | 44502 | 489047.06 | 533549.06 | - | -
60535 | 6 | 605. Program Consultants | 13000000 | 13940822.75 | 68966.25 | 13201142.75 | 13270109 | - | -
60635 | 6 | 606. Revenue Reserve | 0 | 0 | 0 | 0 | 0
|  | Total | 561000000 | 698748532.45 | 79276598.26 | 311513913.705 | 390790511.965