## FY24 Annual
Project Num | Category | DCSD Project Name | DCSD Project Scope of Work | FY 23 Original Estimated Cost | FY 24 Current Estimated Cost (EAC) | Current Year Expenditure | Prior Years Expenditure | Total Expended | Project Status | Estimated Construction Finish
00036 | 1 | 000. Revenue | Project to receive all E-SPLOST VI related revenue from all sources. | 0 | 0 | 0 | 0 | 0 | Non-Construction
10136 | 2 | 101. New Sequoyah MS & Sequoyah HS | Construction of a New Sequoyah Middle School and a New Sequoyah High School (design in E-SPLOST V) | 170000000 | 235000000 | 175000 | 0 | 175000 | Construction | 2028-08-01 | Generator | Cooler/Frezer | Paint | Flooring | Restrooms/fixtures | Kitchen equipment/HVAC | Outside cleaning/painting | Landsacaping | repaving/restriping
10236 | 2 | 102. New Cross Keys MS | Design and construction of a New Cross Keys MS, including purchase of land | 90000000 | 0 | 0 | 0 | 0 | Canceled
20136 | 3 | 201. Allgood ES | HVAC Refresh | 6030000 | 23000000 | 0 | 0 | 0 | Design Procurement | 2027-08-31
20236 | 3 | 202. Ashford Park ES | HVAC Refresh | 5459000 | 18400000 | 0 | 0 | 0 | Design | 2026-05-29
20336 | 3 | 203. Austin ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-07-24
20436 | 3 | 204. Avondale ES | New Security Vestibule | 854000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
20536 | 3 | 205. Barack Obama ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
20636 | 3 | 206. Bob Mathis ES |  | 348000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
20736 | 3 | 207. Briar Vista ES |  | 323000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
20836 | 3 | 208. Briarlake ES | New Security Vestibule | 818000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2027-03-16
20936 | 3 | 209. Brockett ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
21036 | 3 | 210. Browns Mill ES | New Security Vestibule | 868000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
21136 | 3 | 211. Canby Lane ES | New Security Vestibule | 850000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
21336 | 3 | 213. Cedar Grove ES |  | 368000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
21436 | 3 | 214. Chapel Hill ES | New Security Vestibule | 844000 | 500000 | 0 | 0 | 0 | Design | 2026-08-05
21536 | 3 | 215. Chesnut ES |  | 140000 | 0 | 0 | 0 | 0 | Planning | 2027-03-16
21636 | 3 | 216. Columbia ES |  | 367000 | 0 | 0 | 0 | 0 | Planning | 2026-07-17
21736 | 3 | 217. Doraville United ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
21836 | 2 | 218. Dresden ES | Construction of a new Dresden ES facility (design in E-SPLOST V) | 42000000 | 76000000 | 2043753.8 | 0 | 2043753.8 | Construction | 2027-04-12
21936 | 3 | 219. Dunaire ES | New Security Vestibule | 825000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
22036 | 3 | 220. Dunwoody ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
22136 | 3 | 221. E.L. Bouie ES | New Security Vestibule | 915000 | 500000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
22236 | 3 | 222. E. L. Miller ES | New Security Vestibule | 857000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-07-17
22336 | 3 | 223. Evansdale ES | New Security Vestibule | 802000 | 500000 | 0 | 0 | 0 | Design | 2026-08-03
22436 | 3 | 224. Fairington ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
22536 | 3 | 225. Fernbank ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
22636 | 3 | 226. Flat Rock ES | Upgraded Security Vestibule | 664000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
22736 | 3 | 227. Flat Shoals ES | New Security Vestibule | 831000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
22836 | 3 | 228. Hambrick ES |  | 140000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
22936 | 3 | 229. Hawthorne ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
23036 | 3 | 230. Henderson Mill ES | New Security Vestibule | 808000 | 500000 | 0 | 0 | 0 | Planning | 2026-08-31
23136 | 3 | 231. Hightower ES | Roof Replacement, New Security Vestibule | 2343000 | 2500000 | 0 | 0 | 0 | Design | 2025-10-31
23236 | 3 | 232. Huntley Hills ES | New Security Vestibule | 802000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
23336 | 2 | 233. Idlewood ES | HVAC Refresh | 5968000 | 42550000 | 150000 | 0 | 150000 | Construction | 2026-12-30
23436 | 3 | 234. Indian Creek ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
23536 | 3 | 235. John Lewis ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
23636 | 2 | 236. Jolly ES | Roof Replacement, New Security Vestibule | 2946000 | 2600000 | 0 | 0 | 0 | Construction | 2025-10-31
23736 | 3 | 237. Kelley Lake ES | New Security Vestibule | 808000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-18
23836 | 3 | 238. Kingsley ES | New Security Vestibule | 821000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-07-24
23936 | 2 | 239. Kittredge Magnet | Roof Replacement, HVAC Refresh, New Security Vestibule | 7144000 | 23000000 | 0 | 0 | 0 | Construction | 2026-12-01
24036 | 3 | 240. Laurel Ridge ES | New Security Vestibule | 815000 | 500000 | 0 | 0 | 0 | Planning | 2026-04-15
24136 | 3 | 241. Livsey ES | New Security Vestibule | 761000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-18
24236 | 3 | 242. Marbut Theme ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
24336 | 2 | 243. McLendon ES | Roof Replacement, New Security Vestibule | 2290000 | 2300000 | 0 | 0 | 0 | Construction | 2026-05-04
24436 | 3 | 244. Midvale ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Planning | 2026-10-22
24536 | 3 | 245. Montclair ES | New Security Vestibule | 855000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
24636 | 3 | 246. Montgomery ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
24736 | 2 | 247. Murphey Candler ES | HVAC Refresh | 6581000 | 40250000 | 107250 | 0 | 107250 | Design | 2026-07-31
24836 | 3 | 248. Nancy Creek (Former) | New Security Vestibule | 811000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
24936 | 3 | 249. Narvie Harris ES | New Security Vestibule, Gym HVAC Installation | 938000 | 1000000 | 0 | 0 | 0 | Design | 2026-03-04
25036 | 3 | 250. Oak Grove ES |  | 307000 | 0 | 0 | 0 | 0 | Planning | 2027-03-16
25136 | 2 | 251. Oak View ES | Roof Replacement, Upgraded Security Vestibule | 3310000 | 2300000 | 0 | 0 | 0 | Construction | 2026-08-03
25236 | 3 | 252. Oakcliff Theme ES | New Security Vestibule | 857000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
25336 | 3 | 253. Panola Way ES | New Security Vestibule | 899000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
25436 | 3 | 254. Peachcrest ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
25536 | 3 | 255. Pine Ridge ES | New Security Vestibule | 902000 | 500000 | 0 | 0 | 0 | Design | 2026-08-03
25636 | 3 | 256. Pleasantdale ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
25736 | 3 | 257. Princeton ES | Upgraded Security Vestibule | 646000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
25836 | 3 | 258. Rainbow ES |  | 359000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
25936 | 3 | 259. Redan ES | New Security Vestibule | 899000 | 500000 | 0 | 0 | 0 | Design | 2026-08-03
26036 | 3 | 260. Robert Shaw ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
26136 | 3 | 261. Rock Chapel ES | New Security Vestibule | 853000 | 500000 | 0 | 0 | 0 | Planning | 2027-07-07
26236 | 3 | 262. Rockbridge ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
26336 | 3 | 263. Ronald E. McNair DLA ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
26436 | 3 | 264. Rowland ES | New Security Vestibule | 834000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
26536 | 3 | 265. Sagamore Hills ES | New Security Vestibule | 806000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
26636 | 3 | 266. Shadow Rock ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
26736 | 3 | 267. Smoke Rise ES | Upgraded Security Vestibule | 340000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
26836 | 3 | 268. Snapfinger ES | New Security Vestibule | 853000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
26936 | 3 | 269. Stone Mill ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
27036 | 3 | 270. Stone Mountain ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Design | 2026-04-01
27136 | 3 | 271. Stoneview ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
27236 | 3 | 272. Toney ES | New Security Vestibule | 808000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-18
27336 | 3 | 273. Vanderlyn ES |  | 140000 | 0 | 0 | 0 | 0 | Planning | 2027-03-16
27436 | 3 | 274. Wadsworth Magnet |  | 330000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
27536 | 3 | 275. Woodridge ES |  | 315000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
27636 | 3 | 276. Woodward ES | New Security Vestibule | 640000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
27736 | 3 | 277. Wynbrooke ES | New Security Vestibule, Gym HVAC Installation | 925000 | 1100000 | 0 | 0 | 0 | Design | 2026-01-07
30136 | 3 | 301. DeKalb ES of the Arts | New Security Vestibule | 720000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-08-03
30236 | 3 | 302. Cedar Grove MS | New Security Vestibule | 5230000 | 650000 | 0 | 0 | 0 | Design | 2026-08-03
30336 | 2 | 303. Chamblee MS | Roof Replacement, New Security Vestibule | 4350000 | 3150000 | 0 | 0 | 0 | Design | 2026-02-03
30436 | 3 | 304. Champion Theme MS | New Security Vestibule | 1125000 | 650000 | 0 | 0 | 0 | Planning | 2026-09-18
30536 | 3 | 305. Chapel Hill MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-08-03
30636 | 3 | 306. Columbia MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2025-09-03
30736 | 3 | 307. Druid Hills MS |  | 705000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
30836 | 3 | 308. Freedom MS |  | 220000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
30936 | 3 | 309. Henderson MS |  | 859000 | 0 | 0 | 0 | 0 | Planning | 2027-03-16
31036 | 3 | 310. Lithonia MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Planning | 2026-09-18
31136 | 3 | 311. Mary McLeod Bethune MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-08-03
31236 | 3 | 312. Miller Grove MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-08-03
31336 | 3 | 313. Peachtree MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-08-03
31436 | 3 | 314. Redan MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-04-01
31536 | 3 | 315. Ronald E. McNair MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Design | 2026-04-01
31636 | 3 | 316. Salem MS | New Security Vestibule | 1135000 | 650000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
31736 | 3 | 317. Stephenson MS |  | 220000 | 0 | 0 | 0 | 0 | Planning | 2026-04-01
31836 | 3 | 318. Stone Mountain MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
31936 | 3 | 319. Tucker MS | New Security Vestibule | 720000 | 650000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
40136 | 3 | 401. AIC Facility (EAHS and DECA) |  | 310000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
40236 | 3 | 402. Arabia Mountain HS | Upgraded Security Vestibule | 510000 | 500000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
40336 | 3 | 403. Cedar Grove HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
40436 | 3 | 404. Chamblee HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
40536 | 3 | 405. Clarkston HS |  | 310000 | 0 | 0 | 0 | 0 | Planning | 2026-04-15
40636 | 3 | 406. Columbia HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
40736 | 3 | 407. Cross Keys HS |  | 0 | 0 | 0 | 0 | 0 | No Current Scope
40836 | 3 | 408. DeKalb School of the Arts | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Design | 2026-03-05
40936 | 2 | 409. Druid Hills HS | Modernization of the Druid Hills HS Facility | 50000000 | 50000000 | 255000 | 0 | 255000 | Design | 2027-08-13
41036 | 3 | 410. Dunwoody HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
41136 | 3 | 411. Lakeside HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
41236 | 2 | 412. Lithonia HS | Roof Replacement, New Security Vestibule | 7740000 | 4700000 | 0 | 0 | 0 | Construction | 2026-02-03
41336 | 2 | 413. Martin Luther King Jr. HS | Roof Replacement, New Security Vestibule | 5980000 | 3900000 | 0 | 0 | 0 | Construction | 2026-08-03
41436 | 3 | 414. Miller Grove HS | New Security Vestibule | 1569000 | 900000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
41536 | 3 | 415. Redan HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Design | 2026-04-01
41636 | 2 | 416. Ronald E. McNair High | Roof Replacement | 5480000 | 5400000 | 0 | 0 | 0 | Construction | 2025-04-16
41736 | 3 | 417. Southwest DeKalb HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Design | 2026-04-01
41836 | 3 | 418. Stephenson HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Planning | 2026-02-06
41936 | 3 | 419. Stone Mountain HS |  | 310000 | 0 | 0 | 0 | 0 | Planning | 2026-11-13
42036 | 3 | 420. Towers HS | New Security Vestibule | 810000 | 900000 | 0 | 0 | 0 | Design | 2026-04-01
42136 | 3 | 421. Tucker HS | Upgraded Security Vestibule | 510000 | 500000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
50136 | 3 | 501. Coralwood Education | New Security Vestibule | 680000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
50236 | 3 | 502. DeKalb High of Technology South Campus | New Security Vestibule | 680000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-18
50336 | 3 | 503. Eagle Woods Academy | New Security Vestibule | 680000 | 500000 | 0 | 0 | 0 | Construction Procurement | 2026-03-05
50436 | 3 | 504. Early Learning Center at Terry Mill | Upgraded Security Vestibule | 380000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
50536 | 3 | 505. East Campus I/DeKalb Alternative | Upgraded Security Vestibule | 380000 | 200000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
50636 | 3 | 506. Fernbank Science Center | New Security Vestibule | 680000 | 500000 | 0 | 0 | 0 | Design Procurement | 2026-06-30
50736 | 2 | 507. International Student Center | HVAC Refresh | 6060000 | 23000000 | 0 | 0 | 0 | Planning | 2026-03-31
50836 | 2 | 508. Margaret Harris Comprehensive | Roof Replacement, New Security Vestibule | 1890000 | 2000000 | 0 | 0 | 0 | Design | 2026-03-12
50936 | 3 | 509. Warren Technical | New Security Vestibule | 670000 | 500000 | 0 | 0 | 0 | Planning | 2026-09-01
60136 | 3 | 601. Doraville Bus & Administrative |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
60236 | 3 | 602. East Campus II - Transportation |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
60336 | 3 | 603. Green Forest Drive |  | 0 | 0 | 0 | 0 | 0 | No Current Scope
60436 | 3 | 604. Hatton Drive Warehouse |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
60536 | 3 | 605. Panthersville Bu s& Administrative |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
60636 | 3 | 606. Sam A. Moss Service Center |  | 50000 | 0 | 0 | 0 | 0 | No Current Scope
60736 | 3 | 607. William Bradley Bryant Technology Center |  | 45000 | 0 | 0 | 0 | 0 | No Current Scope
60836 | 3 | 608. Old Rock Gym |  | 0 | 0 | 0 | 0 | 0 | No Current Scope
60936 | 3 | 609. Adams Stadium |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
61036 | 3 | 610. Avondale Stadium |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
61136 | 3 | 611. Hallford, James R. Stadium |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
61236 | 3 | 612. North DeKalb Stadium |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
61336 | 3 | 613. William Buck Godfrey Stadium |  | 25000 | 0 | 0 | 0 | 0 | No Current Scope
70136 | 3 | 701. HVAC Controls Upgrade | Upgrade HVAC Controls To Ensure All Schools Meet DCSD Standard: Avondale ES, Brockett ES, Cedar Grove ES, Dunaire ES, Evansdale ES, Flat Rock ES, Flat Shoals ES, Jolly ES, McLendon ES, Narvie Harris ES, Oak Grove ES, Oak View ES, Oakcliff Theme ES, Princeton ES, Ronald E. McNair DLA ES, Rowland ES, Snapfinger ES, Stone Mountain ES, Vanderlyn ES, Woodward ES, Wynbrooke ES, DeKalb ES of the Arts, Cedar Grove MS, Chamblee MS, Columbia MS, Freedom MS, Lithonia MS, Mary McLeod Bethune MS, Peachtree MS, Stone Mountain MS, Arabia Mountain HS, Cedar Grove HS, Chamblee HS, DeKalb School of the Arts, Lakeside HS, Lithonia HS, Redan HS, Ronald E. McNair High, Southwest DeKalb HS, Stone Mountain HS, Towers HS, Tucker HS, East Campus I/DeKalb Alternative, Fernbank Science Center, Margaret Harris Comprehensive, Doraville Bus & Administrative, East Campus II - Transportation, Hatton Drive Warehouse, Panthersville Bus & Administrative, Sam A. Moss Service Center, William Bradley Bryant Technology Center | 0 | 16000000 | 0 | 0 | 0 | Construction Procurement | 2027-08-13
70236 | 3 | 702. Fire Alarm Upgrade | Upgrade Fire Alarms To Ensure All Schools Meet DCSD Standard: Ashford Park ES, Avondale ES, Bob Mathis ES, Briar Vista ES, Briarlake ES, Browns Mill ES, Canby Lane ES, Cedar Grove ES, Chapel Hill ES, Columbia ES, Dunaire ES, E. L. Miller ES, E.L. Bouie ES, Evansdale ES, Flat Rock ES, Flat Shoals ES, Henderson Mill ES, Hightower ES, Huntley Hills ES, Idlewood ES, Jolly ES, Kelley Lake ES, Kingsley ES, Kittredge Magnet, Laurel Ridge ES, Livsey ES, Montclair ES, Murphey Candler ES, Nancy Creek (Former), Narvie Harris ES, Oak Grove ES, Oakcliff Theme ES, Panola Way ES, Pine Ridge ES, Princeton ES, Rainbow ES, Redan ES, Rock Chapel ES, Rowland ES, Sagamore Hills ES, Snapfinger ES, Toney ES, Wadsworth Magnet, Woodridge ES, Wynbrooke ES, Champion Theme MS, Druid Hills MS, Henderson MS, Salem MS, Miller Grove HS | 0 | 13200000 | 0 | 0 | 0 | Design Procurement | 2026-08-03
70336 | 3 | 703. Elevator Cab Rebuild | Rebuild or Replace Elevator Cabs at Select Schools: Columbia ES, Montgomery ES, Rockbridge ES, Rock Chapel ES, Shadow Rock ES, Snapfinger ES, Woodward ES, Champion Theme MS, Cedar Grove HS, Druid Hills HS, Dunwoody HS, Lithonia HS, Martin Luther King Jr. HS, Southwest DeKalb HS | 0 | 8800000 | 0 | 0 | 0 | Construction Procurement | 2025-10-31
80136 | 5 | 801. Bus & Vehicle Purchase | Purchase of Busses and other vehicles as needed. | 35500000 | 35500000 | 0 | 0 | 0 | Non-Construction
80236 | 4 | 802. Device refresh | Replace and purchase computer equipment as needed. | 45000000 | 45000000 | 0 | 0 | 0 | Non-Construction
80336 | 4 | 803. Infrastructure refresh & Support | Update IT infrastructure as needed to support continued District operations. Update at all DCSD Facilities as needed: Security Cameras, Access Control, Intrusion Detection. | 85000000 | 45000000 | 2173429.08 | 0 | 2173429.08 | Construction
80436 | 4 | 804. Update Disaster Recovery Systems | Update disaster recovery systems at DCSD facilities | 1500000 | 1500000 | 0 | 0 | 0 | Planning
80536 | 4 | 805. Update Communication Infrastructure | Update communication infrastructure as needed | 3500000 | 3500000 | 0 | 0 | 0 | Planning
90136 | 1 | 901. Program Management | Management of the E-SPLOST program by third party management as well as other consultants, as required. | 10000000 | 18000000 | 3137454.36 | 2277850.77 | 5415305.13 | Non-Construction
90236 | 1 | 902. DCSD Staff | Salary for District employees in support of the E-SPLOST program | 18000000 | 10000000 | 732393.85 | 557810.98 | 1290204.83 | Non-Construction
99936 | 1 | 999. Program Contingency | Set-aside for unforeseen conditions | 42000000 | 0 | 0 | 0 | 0 | Non-Construction
|  | Total |  | 740000000 | 803400000 | 8774281.09 | 2835661.75 | 11609942.84