## SP6
| MUNIS | E-SPLOST VI | Scope of Work | Phase | Construction Start | Construction Finish
1 | 61036 | Adams Stadium (61036) |  | Non-Construction | 2025-10-30 | 2026-04-15
2 | 40136 | AIC Facility - EAHS and DECA (40136) |  | Planning | 2026-06-01 | 2026-11-13
3 | 20136 | Allgood ES (20136) | HVAC Refresh | Design Procurement | 2025-06-18 | 2027-08-31
4 | 40236 | Arabia Mountain HS (40236) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
5 | 20236 | Ashford Park ES (20236) | HVAC Refresh | Design | 2025-06-13 | 2026-05-29
6 | 20336 | Austin ES (20336) | Upgraded Security Vestibule | Design Procurement | 2025-07-24 | 2026-07-24
7 | 20436 | Avondale ES (20436) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
8 | 61136 | Napoleon B. Cobb Stadium at Avondale Estates (61136) |  | Non-Construction | 2025-10-30 | 2026-04-15
9 | 20536 | Barack Obama ES (20536) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
10 | 20636 | Bob Mathis ES (20636) |  | Planning | 2026-06-01 | 2026-11-13
11 | 20736 | Briar Vista ES (20736) |  | Planning | 2025-10-30 | 2026-04-15
12 | 20836 | Briarlake ES (20836) | New Security Vestibule | Construction Procurement | 2026-09-30 | 2027-03-16
13 | 20936 | Brockett ES (20936) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
14 | 21036 | Brown Mill ES (21036) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
15 | 21136 | Canby Lane ES (21136) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
16 | 21336 | Cedar Grove ES (21336) |  | Planning | 2025-10-30 | 2026-04-15
17 | 40336 | Cedar Grove HS (40336) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
18 | 30236 | Cedar Grove MS (30236) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
19 | 40436 | Chamblee HS (40436) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
20 | 30336 | Chamblee MS (30336) | Roof Replacement, New Security Vestibule | Design | 7/15/2024 A | 2026-02-03
21 | 30436 | Champion Theme MS (30436) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
22 | 21436 | Chapel Hill ES (21436) | New Security Vestibule | Design | 2025-07-31 | 2026-08-05
23 | 30536 | Capel Hill MS (30536) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
24 | 21536 | Chesnut ES (21536) |  | Planning | 2026-09-30 | 2027-03-16
25 | 40536 | Clarkston HS (40536) |  | Planning | 2025-10-30 | 2026-04-15
26 | 21636 | Columbia ES (21636) |  | Planning | 2026-02-02 | 2026-07-17
27 | 40636 | Columbia HS (40636) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
28 | 30636 | Columbia Middle School (30636) | New Security Vestibule | Design | 2025-03-20 | 2025-09-03
29 | 50136 | Coralwood Education (50136) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
30 | 40736 | Cross Keys HS (40736) |  | Planning | 2025-10-30 | 2026-04-15
31 | 30136 | Dekalb ES of the Arts (30136) | New Security Vestibule | Construction Procurement | 2025-08-01 | 2026-08-03
32 | 40836 | Dekalb School of the Arts (40836) | New Security Vestibule | Design | 2025-03-05 | 2026-03-05
33 | 50236 | Dekalb High School of Technology (50236) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
34 | 60136 | Doraville Bus & Administrative (60136) |  | Non-Construction | 2026-09-30 | 2027-03-16
35 | 21736 | Doraville United ES (21736) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
36 | 21836 | Dresden New Replacement Elementary School (21836) | Construction of a new Dresden ES facility (design in E-SPLOST V) | Construction | 05/28/2024 A | 2027-04-12
37 | 40936 | Druid Hill HS Modernization (40936) | Modernization of the Druid Hills HS Facility | Design | 2025-10-13 | 2027-08-13
38 | 30736 | Druid Hills MS (30736) |  | Planning | 2025-10-30 | 2026-04-15
39 | 21936 | Dunaire ES - Safety and Security Upgrades (21936) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
40 | 41036 | Dunwoody HS (41036) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
41 | 22036 | Dunwoody ES (22036) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
42 | 22236 | E. L. Miller ES (22236) | New Security Vestibule | Construction Procurement | 2026-02-02 | 2026-07-17
43 | 22136 | E.L. Bouie ES (22136) | New Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
44 | 20436 | Eagle Woods Academy (20436) | New Security Vestibule | Construction Procurement | 2025-03-27 | 2026-04-01
45 | 50436 | Early Learning Center at Terry (50436) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
46 | 50536 | East Campus I / Dekalb Alternative (50536) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
47 | 60236 | East Campus II - Transportation (60236) |  | Non-Construction | 2026-06-01 | 2026-11-13
48 | 22336 | Evandale ES (22336) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
49 | 22536 | Fernbank ES (22536) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
50 | 22436 | Fairington ES (22436) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
51 | 50636 | Fernbank Science Center (50636) | New Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
52 | 22636 | Flat Rock ES (22636) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
53 | 22736 | Flat Shoals ES (22736) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
54 | 30836 | Freedom MS (30836) |  | Planning | 2025-10-30 | 2026-04-15
55 | 60336 | Green Forest Drive (60336) |  | Non-Construction | 2026-09-30 | 2027-03-16
56 | 61236 | Hallford, James R. Stadium (61236) |  | Non-Construction | 2025-10-30 | 2026-04-15
57 | 22836 | Hambrick ES (22836) |  | Planning | 2026-06-01 | 2026-11-13
58 | 60436 | Hatton Drive Warehouse (60436) |  | Non-Construction | 2025-10-30 | 2026-04-15
59 | 22936 | Hawthorne ES (22936) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
60 | 23036 | Henderson Mill ES (23036) | New Security Vestibule | Planning | 2025-08-29 | 2026-08-31
61 | 30936 | Henderson MS (30936) |  | Planning | 2026-09-30 | 2027-03-16
62 | 23136 | Hightower ES (23136) | Roof Replacement, New Security Vestibule | Design | 2024-10-31 | 2025-10-31
63 | 23236 | Huntley Hills ES (23236) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
64 | 23336 | Idlewood ES (23336) | HVAC Refresh | Construction | 2025-05-27 | 2026-12-30
65 | 23436 | Indian Creak ES (23436) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
66 | 50736 | International Student Center (50736) | HVAC Refresh | Planning | 2025-06-13 | 2026-03-31
67 | 23536 | John Lewis ES (23536) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
68 | 23636 | Jolly ES - Roofing (23636) | Roof Replacement, New Security Vestibule | Construction | 2024-10-31 | 2025-10-31
69 | 23836 | Kingsley Elementary School (23836) | New Security Vestibule | Construction Procurement | 2025-07-24 | 2026-07-24
70 | 23936 | Kittredge Magnet (23936) | Roof Replacement, HVAC Refresh, New Security Vestibule | Construction | 2024-10-31 | 2026-12-01
71 | 23736 | Kelly Lake Elementary Facility (23736) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
72 | 41136 | Lakeside HS (41136) | New Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
73 | 24036 | Laurel Ridge ES (24036) | New Security Vestibule | Planning | 2025-10-30 | 2026-04-15
74 | 41236 | Lithonia HS (41236) | Roof Replacement, New Security Vestibule | Construction | 10/14/2024 A | 2026-02-03
75 | 31036 | Lithonia MS (31036) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
76 | 24136 | Livsey ES (24136) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
77 | 50836 | Margaret Harris Comprehensive (50836) | Roof Replacement, New Security Vestibule | Design | 2024-10-31 | 2026-03-12
78 | 41336 | Martin Luther King Jr. HS (41336) | Roof Replacement, New Security Vestibule | Construction | 10/07/2024 A | 2026-08-03
79 | 24236 | Marbut Theme ES (24236) | New Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
80 | 31136 | Mary McLeod Bethune Middle School (31136) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
81 | 24336 | McLendon ES (24336) | Roof Replacement, New Security Vestibule | Construction | 10/14/2024 A | 2026-05-04
82 | 24436 | Midvale ES (24436) | New Security Vestibule | Planning | 2025-10-22 | 2026-10-22
83 | 31236 | Miller Grove MS (31236) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
84 | 41436 | Miller Grive HS (41436) | New Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
85 | 24536 | Montclair ES (24536) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
86 | 24636 | Montgomery ES (24636) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
87 | 24736 | Murphey Candler ES (24736) | HVAC Refresh | Design | 2025-05-27 | 2026-07-31
88 | 24936 | Narvie Harris (24936) | New Security Vestibule, Gym HVAC Installation | Design | 2025-09-18 | 2026-03-04
89 | 10136 | New MS & HS at Sequoyah HS (10136) | Construction of a New Sequoyah Middle School and a New Sequoyah High School (design in E-SPLOST V) | Construction | 06/12/2024 A | 2028-08-01
90 | 61336 | North DeKalb Stadium (61336) |  | Non-Construction | 2026-02-02 | 2026-07-17
91 | 25036 | Oak Grove ES (25036) |  | Planning | 2026-09-30 | 2027-03-16
92 | 25136 | Oak View ES (25136) | Roof Replacement, Upgraded Security Vestibule | Construction | 2024-11-04 | 2026-08-03
93 | 25236 | Oakcliff Themed ES (25236) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
94 | 60936 | Old Rock Gym (60936) |  | Non-Construction | 2026-09-30 | 2027-03-16
95 | 25336 | Panola Way ES (25336) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
96 | 60536 | Panthersville Bus & Administrative (60536) |  | Non-Construction | 2026-02-02 | 2026-07-17
97 | 25636 | Pleasantdale ES (25636) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
98 | 31336 | Peachtree MS (31336) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
99 | 25436 | Peachcrest ES (25436) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
100 | 25536 | Pine Ridge ES (25536) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
101 | 25736 | Princeton ES (25736) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
102 | 25836 | Rainbow ES (25836) |  | Planning | 2026-06-01 | 2026-11-13
103 | 31436 | Redan MS (31436) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
104 | 25936 | Redan ES (25936) | New Security Vestibule | Design | 2025-08-01 | 2026-08-03
105 | 41536 | Redan HS (41536) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
106 | 26036 | Robert Shaw Theme ES (26036) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
107 | 26236 | Rockbridge ES (26236) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
108 | 26136 | Rock Chapel Elementary School (26136) | New Security Vestibule | Planning | 2026-07-09 | 2027-07-07
109 | 26336 | Ronald E. McNair (26336) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
110 | 41636 | Ronald E. McNair High (41636) | Roof Replacement | Construction | 10/09/2024 A | 2025-04-16
111 | 31536 | Ronald E. McNair MS (31536) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
112 | 26436 | Rowland ES (26436) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
113 | 26536 | Sagamore Hills ES (26536) | New Security Vestibule | Planning | 2025-08-27 | 2026-09-01
114 | 31636 | Salem MS (31636) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
115 | 60636 | Sam A. Moss Service Center (60636) |  | Non-Construction | 2026-09-30 | 2027-03-16
116 | 26636 | Shadow Rock ES (26636) | New Security Vestibule | Planning | 2025-08-27 | 2026-09-01
117 | 60836 | Silver Hill Road (60836) |  | Non-Construction | 2026-09-30 | 2027-03-16
118 | 26736 | Smoke Rise ES (26736) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
119 | 26836 | Snapfinger ES (26836) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
120 | 41736 | Southwest Dekalb HS (41736) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
121 | 31736 | Stephenson MS (31736) |  | Planning | 2025-03-27 | 2026-04-01
122 | 41836 | Stephenson HS (41836) | New Security Vestibule | Planning | 2025-08-25 | 2026-02-06
123 | 26936 | Stone Mill ES (26936) | New Security Vestibule | Planning | 2025-08-27 | 2026-09-01
124 | 27036 | Stone Mountain (27036) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
125 | 41936 | Stone Mountain High School (41936) |  | Planning | 2026-06-01 | 2026-11-13
126 | 31836 | Stone Mountain MS (31836) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
127 | 27236 | Toney ES (27236) | New Security Vestibule | Planning | 2025-09-18 | 2026-09-18
128 | 42036 | Tower HS (42036) | New Security Vestibule | Design | 2025-03-27 | 2026-04-01
129 | 31936 | Tucker MS (31936) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
130 | 42136 | Tucker HS (42136) | Upgraded Security Vestibule | Design Procurement | 2025-06-30 | 2026-06-30
131 | 27336 | Vanderlyn ES (27336) |  | Planning | 2026-09-30 | 2027-03-16
132 | 27436 | Wadsworth Magnet (27436) |  | Planning | 2026-06-01 | 2026-11-13
133 | 50936 | Warren Technical (50936) | New Security Vestibule | Planning | 2025-08-27 | 2026-09-01
134 | 60736 | William Bradley Bryant Technology Center (60736) |  | Non-Construction | 2026-09-30 | 2027-03-16
135 | 61436 | William Buck Godfrey Stadium (61436) |  | Non-Construction | 2026-02-02 | 2026-07-17
136 | 27536 | Woodridge ES (27536) |  | Planning | 2025-10-30 | 2026-04-15
137 | 27636 | Woodward Elementary School (27636) | New Security Vestibule | Construction Procurement | 2025-03-05 | 2026-03-05
138 | 27736 | Wynbrooke ES (27736) | New Security Vestibule, Gym HVAC Installation | Design | 2025-07-24 | 2026-01-07