## Slide 1
Organizational Review
& Efficiency Study
Board Status Update | Phase 3 Findings
Bibb County School District
March 2026
LEAN Frog Consulting | www.theleanleap.com

## Slide 2
Engagement Overview
Per RFP #25-041: Organizational and Efficiency Study
1
Initiation &
Planning
Project objectives, communication protocols, data requirements, interview guides
Complete
2
Data Collection
& Engagement
Stakeholder interviews, process walkthroughs, PPM Maturity Assessments
Complete
3
Benchmarking &
Comparative Analysis
Peer comparisons, performance review, efficiency opportunity identification
Current Phase
4
Recommendations
& Cost Analysis
Implementable recommendations, action planning, fiscal impact analysis
Upcoming
Current Status: BCSD is in the Phase 3 review point. Current state findings and opportunities are being reviewed prior to development of detailed recommendations in Phase 4.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
2

## Slide 3
Project Team & Methodology
LEAN Frog Project Team
Byron Headrick, MBB
Principal Consultant
Sherri Headrick, Ph.D.
Principal Consultant
Mary Marquart
Lean Consultant
Beth Stephens
Data Contact
LEAN Frog Data Team
Additional support as needed
Data Sources & Methods
Stakeholder interviews with department leadership and operational staff
Process walkthroughs and PPM Maturity Level Assessments across 10 departments
3-year financial and staffing trend analysis (SY 22-23 through SY 24-25)
Review of department performance metrics, cost benchmarks, and operational KPIs against national and regional standards
LEAN Frog proprietary database: 155+ school systems for national and regional benchmarking
Three peer district groups: size-based, requested, and high-performing Georgia systems
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
3

## Slide 4
Departments Assessed
10 non-instructional departments evaluated across organizational structure, staffing, processes, and performance
Human Resources
18 positions
Finance
33 positions
Facilities & Maintenance
46 FTE + 169 custodians
Transportation
198 FTE
School Nutrition
Central + site-based
Technology
82 FTE (incl. media)
Safety & Risk Mgmt
2.5 FTE
Campus Police (Area Added during Project)
69 positions
Athletics (Area Added during Project)
4 central + school-based
District Effectiveness
& Federal Programs (Area Added during Project)
45 positions
Each department was evaluated using: Span of Control Analysis | PPM Maturity Assessment | Peer Benchmarking | 3-Year Performance and Finical Trend Analysis | Process Walkthroughs
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
4

## Slide 5
Peer Districts and Funding Context
Peer Group | Districts | Selection Basis
Size-Based | Carroll, Coweta, Douglas, Fayette, Newton | Similar enrollment and demographics in Georgia
Requested | Clayton, Henry, Muscogee, Newton, Richmond, | Requested by BCSD for organizational comparison
High-Performing | Fayette, Forsyth, Morgan, Lowndes, Oconee | High-performing Georgia county systems
Why Funding Mix Matters
Bibb leads the peer set on federal funding intensity: 13.9% of total revenue from federal sources and approximately $2,152 per FTE. Most peers range from 2% to 8%.
Higher federal funding drives denser staffing ratios. This is by design. Federal dollars fund additional academic support, intervention, and compliance positions that inflate total headcount relative to low-federal peers.
Peer comparisons in this report account for this context. Comparisons are data-based, not prescriptive. Where funding mix explains a difference, the analysis notes it.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
5

## Slide 6
Key Definitions
Terms and frameworks referenced throughout this presentation
Span of Control
A framework for evaluating supervisory capacity using 8 indicators (experience, mastery, activity type, metrics, routine nature, standardization, leadership focus, and proximity). Not a headcount ratio. It measures how effectively a given structure can manage its workload.
PPM Maturity Level
Process and Performance Management Maturity. A 5-level scale (Ad Hoc, Fragmented, Defined, Managed, Optimizing) that measures how consistently processes are documented, executed, measured, and improved. Most BCSD departments assessed at Defined (Level 3).
Peer Benchmarking
Data-based comparison of staffing ratios, cost metrics, and performance indicators against comparable districts. Benchmarking identifies where BCSD falls relative to peers. It does not prescribe action without process-level context.
Process Maturity vs. Cross-Functional Friction
A diagnostic that plots each department on two dimensions: how mature its internal processes are, and how much coordination burden it creates for other departments. High-friction departments consume resources across the organization, regardless of their internal discipline.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
6

## Slide 7
The Executive Reality
People Compensating for System Gaps
Fragmented
Workflows
Core support functions operate through fragmented handoffs. Departments work effectively in their own lanes, but enterprise-wide tasks rely on nonstandard, manual coordination.
Split
Accountability
Current structural alignment does not consistently support efficient execution. Split authority and function placement create avoidable coordination burdens.
Uneven Management
Infrastructure
While some departments exhibit strong process discipline, others remain defined but unmanaged, lacking metrics, standard cycle times, and closed-loop follow-up.
District performance depends too heavily on institutional knowledge and individual effort rather than fully integrated workflows.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
7

## Slide 8
The Cost of Manual Coordination
What Manual Coordination Looks Like
Spreadsheets used as primary workflow tools between departments
Duplicate data entry across disconnected systems (PowerSchool, Munis, ConApp, Incident IQ)
Manual verification replacing automated integration
Undocumented institutional knowledge as the operating system
Paper-based routing for travel reimbursements, P-Card reconciliation, and timekeeping
What Integration Enables
Standardized workflows reduce rework and eliminate redundant positions over time
Technology handles routine transactions, freeing staff for higher-value work
Data flows between systems without manual re-entry
Processes are documented and transferable, reducing single-point-of-failure risk
Departments share common metrics and accountability frameworks
Efficiency opportunities are not limited to headcount. A meaningful share of current workload is artificially created by rework and broken systems. Process redesign must precede any broad staffing reductions.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
8

## Slide 9
The Financial Squeeze
The Margin of Error Has Evaporated
Chart: 
| SY 19-20 | SY 22-23 | SY 23-24 | SY 24-25
Per-Pupil Revenue | 10105 | 10518 | 11784 | 12989
Per-Pupil Expenditure | 9715 | 10584 | 11682 | 13147
-$158
Per Pupil Deficit (SY 24-25)
2.2%
Enrollment decline
(5 years)
32.4%
Expenditure growth
(5 years)
14.6%
Total staff decline
(5 years)
For the first time in the analysis period, per-pupil operating costs have eclipsed per-pupil revenues. Enrollment has declined 2.2% while total staff declined 14.6%, yet expenditures have accelerated by 32.4% overall.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
9

## Slide 10
Acute Continuity Risk
The Impending Retirement Transition
28%
eligible within
5 years
13% eligible right now
across all departments studied
Highest Retirement Exposure by Department
% eligible within 5 years
Facilities & Maintenance
38%
Specialized trades, 42-year predecessor just replaced
Finance
35%
Warehouse and entry-level accounting most exposed
Transportation
29%
Largest absolute count (56 positions); two of five Route Supervisors eligible
School Nutrition
27%
Executive Director already vacant; leadership under dual pressure
The departments with the highest near-term retirement exposure are the same departments identified as most reliant on undocumented institutional knowledge. When these individuals leave, the manual systems will collapse.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
10

## Slide 11
Departmental Diagnostic
Process Maturity vs. Cross-Functional Friction
Disciplined / Managed
Ad Hoc / Informal
Isolated Execution
Heavy Reliance on Handoffs
Process
Maturity
Cross-Functional Friction
District Eff.
& Federal Pgms
Technology is not currently resourced to support the automation, integration, and AI improvements identified across other departments.
Clear ownership,
documented processes
Strong internal controls, bottlenecked
by cross-department integration
Operationally workable through
committed staff, but lacks
data-driven management
Split authority, manual follow-up,
structural/financial pressure
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
12
Transport.
Athletics
Facilities
School
Nutrition
Safety &
Risk Mgmt
Campus
Police
Technology
HR
Finance

## Slide 12
Human Resources
Staffing, cost, and performance benchmarks (SY 24-25)
PPM Maturity DEFINED
Metric | BCSD | SE Regional | National | Peer Range | Signal
Staff per HR Employee | 181 | 225 (SE avg) | 325 | 152-469 | Above most peers
HR Cost per District Staff | $732 | $545 | $826 | -- | Below national
Overall Separation Rate | 17.0% | 16.3% | 14.2% | -- | Above both
Teacher Separation Rate | 16.8% | 15.9% | 11.9% | -- | Above both
Misconduct per 1K Staff | 19.4 | 5.7 | 18.5 | -- | 3.4x regional
HR Cost 3-Year Change | +27% | -- | -- | -- | Rising
Staffing ratio exceeds peers, but cost per staff is below national. High headcount of lower-paid staff compensating for manual processes.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
13

## Slide 13
Human Resources: Opportunities
Key Opportunities Identified
Automate high-volume manual processes
Travel reimbursement, leave management, and athletic supplement processing can be streamlined without system integration.
Address the Compensation Specialist role bottleneck
Five incumbents since 2021. Role is structurally overloaded managing supplements across 25+ budget codes. Redesign required.
Build workforce analytics capability
Separation rates exceed all benchmarks and are trending upward. The district cannot diagnose root cause with a 10% exit survey response rate.
Leverage the leadership transition
The pending Asst. Superintendent retirement creates a restructuring window. If the Executive Director assumes the role, the Asst. Supt. line may not need to be refilled.
Standardize principal compliance with HR procedures
Principals are not consistently following required coaching and documentation steps before termination. Being codified in board policy.
Resolve split Workers' Comp accountability
Workers' Comp straddles HR and Safety & Security with unclear ownership. Consolidate under one authority.
HR operates with documented processes but is constrained by system integration gaps and a staffing model built to manage manual work rather than drive strategic improvement.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
14

## Slide 14
Finance
Staffing, cost, and performance benchmarks (SY 24-25)
PPM Maturity DEFINED
Metric | BCSD | SE Regional | National | Peer Range | Signal
Revenue per Finance Staff | $12.35M | -- | -- | $16-30M | Lowest among peers
Procurement Cost per $100K Rev | $324 | $112 | $87 | -- | 3-4x benchmarks
Cost per Purchase Order | $104 | -- | $63 | -- | 65% above national
Paycheck Error Rate (per 10K) | 9.74 | -- | 9.8 | -- | At parity (was 63.5)
Payroll Cost 3-Year Change | +32% | -- | -- | -- | Rising faster than rev
Expenditure Efficiency (Budget/Actual) | 97.1% | -- | 113.7% | -- | Better than the median of national peers. Minimal budget cushion
Note: BCSD is the only peer housing warehouse operations under Finance. Warehouse staff excluded from ratios above, except for Procurement Cost. Grants management placement varies across peers (4 of 10 peers also house grants under Finance) and is not an outlier.
Payroll accuracy improved dramatically: errors dropped from 63.5 to 9.74 per 10K payments over two years.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
15

## Slide 15
Finance: Opportunities
Key Opportunities Identified
Digitize travel reimbursement
Entirely paper-based using internal courier. Finance leadership independently identified this as a pain point. Highest-impact quick win.
Eliminate parallel P-Card reconciliation
Paper receipts and digital workflows run in parallel. Consolidating to a single digital process removes redundant verification steps.
Resolve blended-rate timekeeping gap
Tyler T&A cannot handle multi-funding-source employees. Finance staff physically drive to schools to collect timesheets. System fix or workaround needed.
Reduce cross-system data re-entry
Grant budgets maintained in both Munis and ConApp. Fixed assets in Incident IQ. No data sharing between systems. Each re-entry point is an error risk.
Realign warehouse to Operations
BCSD is the only peer housing warehouse under Finance. Realignment would reduce procurement cost ratios and match peer organizational models.
Use retirement timing for organic restructuring
42% of department (12 eligible + 2 vacancies) will turn over within 5 years, concentrated in roles most affected by automation.
Finance operates with strong controls and improving accuracy but carries the lowest revenue-per-staff ratio among all peers, driven by paper-based workflows.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
16

## Slide 16
Facilities & Maintenance
Cost, workload, and staffing benchmarks (SY 24-25)
PPM Maturity DEFINED
Metric | BCSD | SE Regional | National | Signal
Maintenance Cost / Sq Ft | $0.67 | $3.50 | $1.35 | 50% below national
Custodial Cost / Sq Ft | $1.64 | $1.44 | $1.88 | Between benchmarks
Utility Cost / Sq Ft | $1.43 | -- | $1.36 | Above national
Avg Days to Complete WO | 6.9 | -- | 18.0 | Strong performance
Work Orders per Technician | 161.9 | -- | 206 (median) | Below median
Sq Ft per Custodian | 25,660 | 40,137 | 24,909 | High density vs. regional
Retirement Eligible (5 yr) | 39% | -- | -- | Highest in study
Below-benchmark maintenance costs are a warning signal, not proof of efficiency. Without a facility condition assessment, the district cannot determine whether low spending reflects efficiency or deferred maintenance.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
17

## Slide 17
Facilities & Maintenance: Opportunities
Key Opportunities Identified
Conduct a Facility Condition Assessment
No FCA exists. The district cannot quantify deferred maintenance, prioritize capital, or right-size the workforce without this baseline. Prerequisite to all other decisions.
Complete Incident IQ deployment
Work order system only 5-6 months old. Asset tagging in progress. Labor-hour tracking not yet systematic. Full deployment enables data-driven staffing decisions.
Rebalance custodial staffing across school types
Middle and high schools are overstaffed vs. benchmarks while elementary schools are at or above recommended ranges. Redistribution, not reduction.
Transition supervisors from task execution to management
Supervisors close tickets rather than technicians. Frontline leadership consumed by task-level work instead of managing workflow and quality.
Standardize custodial cleaning frequencies and task-based workloading
No documented cleaning standards by space type. No task-based time standards. Principals redirect custodians to non-cleaning duties.
Develop succession plans ahead of the 39% retirement cliff
Highest retirement exposure in the study. Specialized trades cannot be cross-trained quickly. Knowledge documentation must precede departures.
Low maintenance spending is a warning signal, not a strength. The FCA is the prerequisite to any staffing, capital, or structural decision in this department.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
18

## Slide 18
Transportation
Cost, fleet, and operational benchmarks (SY 24-25)
PPM Maturity DEFINED
Metric | BCSD | SE Regional | National | Signal
Cost per Bus | $41,308 | -- | $77,063 | Well below national
Cost per Rider | $808 | -- | $1,354 | Well below national
Cost per Mile | $3.93 | -- | $6.42 | Well below national
Students per Daily Run Bus | 74.9 | 42.2 | -- | Strong efficiency
Spare Bus Ratio | 31.7% | 19.0% | -- | Above (declining from 40%)
Buses per Mechanic | 24.9 | 23.5 | 30:1 std | Within threshold
Retirement Eligible (5 yr) | 28% | -- | -- | Largest absolute count
Cost efficiency is sustained by people, not yet by systems. Traversa, Fleet Vision, Fuel Master, and GeoTab are available but significantly underutilized.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
19

## Slide 19
Transportation: Opportunities
Key Opportunities Identified
Activate underutilized software systems
Four systems purchased but not fully deployed. Parts and labor not consistently charged in Fleet Vision. Ridership scan data incomplete. Tools exist; usage does not.
Plan for enrollment-driven route optimization
Projected enrollment decline (~890 fewer students for SY 26-27) will reduce ridership and create pressure to consolidate routes. Proactive optimization preserves cost efficiency; reactive cuts risk service disruption.
Stabilize Fleet Manager position
Three turnovers in 18 months. 4 of 9 mechanics are newer. Leadership instability limits process standardization and long-term fleet planning.
Address the split-compound coordination cost
Drivers at Roff, central staff at Cavalier. Two supervisors and two mechanics travel daily between sites. Shop consolidation is underway and will reduce this friction.
Build succession plans for retirement-eligible supervisors
Two Regular Ed Route Supervisors are retirement-eligible. Institutional knowledge of routes, students, and school relationships is at risk.
Commendation: cost efficiency, full driver allotment, and shop consolidation
Cost per bus, rider, and mile are all well below benchmarks. Full driver allotment achieved for the first time in 14 years. The in-progress shop consolidation reflects proactive operational improvement.
Transportation delivers strong cost performance. Declining enrollment will require proactive route optimization to maintain efficiency. The in-progress shop consolidation is a positive step toward reducing operational friction.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
20
Continue fleet right-sizing through planned scrapping
Spare ratio (31.7%) declining from 40.1% as buses are scrapped. Continue to target industry-standard 15-20% spare ratio.

## Slide 20
School Nutrition
Financial performance and operational benchmarks (SY 24-25)
PPM Maturity DEFINED
Metric | BCSD | SE Regional | National | Signal
Fund Balance (% of Revenue) | 18.8% | 41.1% | 29.3% | Below both benchmarks
Fund Balance 2-Year Change | -53% | -- | -- | Rapid erosion
Food Cost (% of Revenue) | 75.3% | 34.6% | 42.3% | Critical outlier
Total Cost per Meal | $6.51 | $4.35 | $4.86 | Above both benchmarks
Labor Cost (% of Revenue) | 47.5% | 39.4% | 45.6% | Above both benchmarks
District-wide MPLH | 17.03 | 17.6 | 14.0 | Competitive overall
Elementary MPLH Range | 13.5 - 27.1 | -- | -- | 2x site-level variance
Food costs rose from 50.8% to 75.3% of revenue in two years, the primary driver of fund balance erosion. Three critical leadership positions are currently vacant.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
21

## Slide 21
School Nutrition: Opportunities
Key Opportunities Identified
Stabilize inventory controls (in progress)
Biweekly ordering, discard reports, and cycle counts recently implemented. Not yet mature. Inventory loss was not consistently documented historically.
Conduct site-level MPLH optimization review
Elementary MPLH ranges from 13.5 to 27.1 across 21 schools. Variation does not correlate with enrollment or participation. Labor hours may not be aligned to meal volume.
Address competitive food revenue leakage
School-level competitive food sales reduce cafeteria participation and federal reimbursement revenue. Each student diverted is lost USDA reimbursement.
Fill critical leadership vacancies
Executive Director, Training Specialist, and Nutrition Site Support-Technology Services are all vacant. Budget Manager serving dual roles. Department cannot execute improvement under this structure.
Fully leverage LINQ system capabilities
LINQ supports POS, inventory, menu management, and ordering, but manual processes remain common. Master departmental schedule not consistently followed.
Eliminate off-site commercial freezer dependency
Limited on-site capacity requires external storage adding cost and logistics complexity. Vendor delivery schedule adjustments underway.
School Nutrition is in financial distress driven by food cost escalation and inventory control gaps. Stabilization is underway, but recovery requires addressing food costs, labor alignment, and leadership vacancies.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
22

## Slide 22
Technology
Infrastructure, staffing, and investment benchmarks (SY 24-25)
PPM Maturity MANAGED
Metric | BCSD | SE Regional | National | Signal
Network Bandwidth (Mbit/s/student) | 1.87 | 577.4 | 248.4 | Critical gap
Devices per Student | 1.75 | -- | 1.40 | Above benchmark
IT Spend per Student | $363 | $528 | $349 | Between benchmarks
Capital IT Spend (3-Yr Change) | -82% | -- | -- | $10M to $1.8M
Devices Managed (3-Yr Change) | +10.8% | -- | -- | Fleet growing
Days Network > 75% Capacity | 10 | -- | 5.0 | 2x national average
Technology is the only department rated at Managed maturity. The critical infrastructure gap is network bandwidth. Capital spending decline may be building a device refresh cliff.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
23

## Slide 23
Technology: Opportunities
Key Opportunities Identified
Address the network bandwidth gap
At 1.87 Mbit/s per student vs. 248.4 nationally, this is the largest infrastructure gap in the study. Bandwidth limits the return on every device and software investment.
Resource the department for internal business system integration
Technology is oriented toward student-facing device management. The automation, integration, and AI improvements identified across other departments require internal IT capacity that does not currently exist.
Evaluate the capital spending trajectory
Capital IT dropped 82% over 3 years while devices grew 10.8%. If this reflects deferred investment rather than ESSER completion, a refresh cliff is forming.
Centralize device imaging and deployment
Technicians image devices at individual schools with no centralized staging. This increases variability, extends timelines, and adds to technician workload.
Reduce CIO operational stretch
CIO directly manages four functional areas and is personally involved in acquisition decisions. Senior Analyst is the sole Tableau resource, creating a single point of failure.
Standardize school-level support request processes
Schools vary in how they initiate tickets. Some bypass Incident IQ entirely. Inconsistent intake reduces visibility and prevents workload analysis.
Technology demonstrates strong governance and maturity. The critical risks are bandwidth infrastructure, capital spending trajectory, and the gap between current staffing and the district's cross-department integration needs.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
24

## Slide 24
Safety & Security / Campus Police
The Split Authority Challenge
Safety & Security PPM DEFINED
Police PPM FRAGMENTED
Metric | BCSD | National Avg | Signal
Combined Staff per 1K Students | 3.26 | 1.70 | Nearly 2x national
Patrol Officers (3-Yr Growth) | 10 to 27 | -- | Tripled
Assault/Battery per 1K Students | 6.61 | 4.60 | 44% above national
Bullying/Harassment per 1K | 0.05 | 2.30 | Possible classification variance
Alarm-Equipped Sites | 14% | 99% | Largest infrastructure gap
Drills per Crisis Team | 19.36 | 9.60 | Double benchmark
Training Hours per Personnel | 38.4 | 31.1 | Above benchmark
Campus Police is the only department rated at Fragmented maturity. Patrol staffing tripled in three years, but no department-level KPIs, trend analysis, or standardized incident response protocols exist. Incident engagement varies by school. The staffing investment lacks systems to measure its impact.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
25

## Slide 25
Safety & Campus Police: Opportunities
Key Opportunities Identified
Establish unified safety governance structure
Campus Police, Safety & Risk Management, and Student Affairs operate with overlapping authority and no shared accountability framework. Define decision rights and reporting relationships.
Standardize incident response protocols district-wide
When and how Campus Police is engaged varies by administrator. Identical student behavior produces different outcomes by school. Creates equity and legal risk.
Build a shared data and analytics platform
Incident data split across RMS/CAD, Infinite Campus, and other systems. No aggregation, no dashboard, no trend analysis. Cannot measure whether the staffing investment is working.
Address the physical security infrastructure gap
Only 14% of sites have alarm systems vs. 99% nationally. Zero intrusions is a positive outcome, but technology investment could reduce reliance on personnel-based coverage.
Connect safety to student services and behavior intervention
The current model is reactive. Connecting campus police deployment to restorative practices and early intervention would shift from response to prevention.
Develop process documentation before retirement losses
Campus Police at Fragmented maturity means knowledge lives in people. 21% retirement eligible within 5 years. Processes must be captured now.
The primary issue is not staffing presence but role clarity and decision consistency. Avoidable burden is created across the district because authority lanes overlap without clear end-to-end accountability.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
26

## Slide 26
Athletics: Opportunities
Key Opportunities Identified
Update coaching supplement rates (frozen since 1997)
Nearly 30-year-old rate structure creates manual complexity across Athletics, HR, and Finance. Classified employees receive lump-sum payments requiring separate processing.
Reduce single-person operational dependencies
With 4 central FTE (effectively 3 with Wellness Center vacant), multiple workflows depend on one person. Work distribution and documentation needed.
Standardize middle school eligibility documentation
High school eligibility managed through GHSA portals. Middle school eligibility uses district criteria with varying documentation practices. Not centrally audited.
Evaluate athletics maintenance alignment with Facilities
Separate maintenance supervisor, grounds crew, and work order system. Consolidating under Facilities could improve coordination and resource sharing.
Establish department KPIs and service-level standards
No formal athletic KPIs exist. Performance inferred from operational outcomes. Define turnaround expectations and measurable service standards.
Athletics operates with experienced, committed staff but lacks documented processes, performance metrics, and modern supplement structures. Costs are stable at 0.6% of district expenditures.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
27

## Slide 27
District Effectiveness: Opportunities
Key Opportunities Identified
Document processes before institutional knowledge is lost
~60% of team assumed current roles within 2 years. Managed maturity is sustained by senior leadership knowledge, not yet by formalized documentation.
Plan for the ESSER funding cliff
Grant-funded staff grew from 3.1% to 15.1% of district FTEs. 490 positions need to be sustained, reduced, or eliminated as pandemic-era funding expires.
Shift from compliance-driven to outcome-driven measurement
The department tracks budgets, compliance, and reimbursements systematically. Outcome evidence exists (e.g., program examples, recognitions, individual success stories, etc.) but systematic measures remain underdeveloped.
Monitor declining competitive grant capacity
Competitive grants dropped 14.7% year-over-year. As formula ESSER funds expire, competitive grant-writing becomes more critical to sustaining programs.
Commendation: 99.75% grant utilization rate
Only $117K of $47M returned in SY 24-25. This reflects exceptional fiscal management and compliance discipline. Strongest department in the study.
District Effectiveness is the highest-performing department in this study. The risks are succession, the ESSER cliff, and the transition from compliance-driven to outcome-driven management.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
28

## Slide 28
The Strategic Reality
You Cannot Right-Size a Fragmented System
Financial
Squeeze
+
Fragmented
Workflows
=
System
Failure
The district's high operating costs are a symptom of inefficient workflows, not just overstaffing. Attempting broad headcount reductions disconnected from workflow changes will break the manual systems holding the district together.
The Required Sequence
Stabilize Current
Operations
>>>
Process
Redesign
>>>
Right-Size for
Fiscal Reality
Takeaway: Process redesign must precede or accompany any staffing decisions.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
29

## Slide 29
The Architecture of Reform
A Three-Phase Sequence
1
Phase 1: Clarify & Stabilize
Clarify ownership and stabilize least mature areas. Use current vacancies and near-term retirements as natural entry points for structural refinement. Document workflows during transitions, then redesign roles to match improved processes rather than backfilling as-is.
2
Phase 2: Simplify & Align
Redesign cross-department workflows, automate highest-friction manual processes, and align restructured roles with redesigned work. Strengthen KPIs and build shared data infrastructure to support ongoing management.
3
Phase 3: Right-Size & Sustain
Evaluate staffing alignment post-redesign, leverage automation and continued natural attrition, and confirm impact with data before making structural changes permanent. Sustainability is the measure, not speed.
Guiding Principles
Simplify work before reducing capacity
Clarify accountability before redesigning structure
Use data to confirm impact
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
30

## Slide 30
Immediate Priorities
Executing Phase 1: Stabilize
Use the Retirement Window
for Structural Refinement
The 28-39% retirement exposure in Facilities, Transportation, and Finance creates a natural restructuring window. Rather than backfilling positions as they stand, redesign roles and workflows first, then staff to the improved model. Document institutional knowledge as part of the redesign process.
Untangle the Handoffs
Target the HR and Finance chasm. Standardize the highest-friction workflows that create manual transaction burden and duplicate entry. Begin with travel reimbursement, supplement processing, and leave management as early-impact improvements that demonstrate the redesign-before-reduction approach.
Clarify Safety Ownership
Establish clean, linear reporting relationships and definitive decision rights across Campus Police, Safety, and Student Affairs to eliminate the split authority trap. Build shared data and a unified improvement cycle connecting security presence to student behavior intervention.
The window for proactive restructuring is open, but narrowing. Execution must begin with stabilizing the core.
LEAN Frog Consulting | www.theleanleap.com
Bibb County School District | Board Status Update | March 2026
31

## Slide 31
Next Steps
Moving from Findings to Recommendations
1
Gather Board Input
Today's presentation provides the status of Phase 3 findings and identified opportunities. The Board's questions, priorities, and concerns will inform how recommendations are developed.
2
Engage District Leadership
Work with the Superintendent's team to review findings, validate observations, and align on which opportunities are most impactful and implementable for Bibb County.
3
Collaborate with Department Teams
The people in operational roles hold detailed knowledge of how work is actually done. Recommendations must reflect their input to ensure they can be implemented and sustained.
4
Develop Detailed Recommendations
Phase 4 will translate findings into implementable recommendations with action plans, sequencing, and fiscal impact analysis. The goal is not just what to change, but how to change it in a way the district can execute and sustain.
This presentation represents Phase 3 findings and identified opportunities. It is not a final report. Detailed recommendations will be developed in Phase 4 in collaboration with district leadership.
LEAN Frog Consulting | www.theleanleap.com
32